## Sheet1
Id	Project	Reporter	Assigned To	Priority	Severity	Estimates Time	Developer	Category	Date Submitted	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version
41	Nacalle	administrator	Ihab Roshdy	normal	major	2 days		Development	2015-07-08				public	2015-07-08	@admin: when i edit in an event of type non to SMS, no action is taken	new	open
40	Nacalle	administrator	Ihab Roshdy	normal	minor	4 hours		Development	2015-07-02				public	2015-07-02	when is search with empty text box in people attended, the page design crashes	new	open
39	Nacalle	administrator	Omar Khaled	normal	minor	4 hours		Development	2015-07-02				public	2015-07-02	on making new reservation , the list should be arranged with unreserved guests first	new	open
37	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-07-01				public	2015-07-01	after i check in a guest, i am not redirected to check in page	new	open
34	Nacalle	administrator	Ihab Roshdy	normal	major	2 days		Development	2015-07-01				public	2015-07-01	@admin: i can't add a new reservation with units (seating status)	new	open
33	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-06-23				public	2015-06-23	@admin: when i add new guest on reservation, the reservations details erase and i am directed to events page	new	open
31	Nacalle	administrator	Omar Khaled	normal	crash	4 hours		Development	2015-06-23				public	2015-06-23	@vendor: when i add a new guest with existing mobile, the portal crashes	new	open
30	Nacalle	administrator	Ihab Roshdy	normal	minor	4 hours		Development	2015-06-22				public	2015-06-22	@admin: when i reserve to a guest, the serch box required design is invalid	new	open
29	Nacalle	administrator	Ihab Roshdy	normal	major	2 days		Development	2015-06-22				public	2015-06-22	@vendor: invitation SMS doesn't arrive	new	open
23	Nacalle	administrator	Omar Hammad	normal	minor	2 days		Development	2015-06-15				public	2015-06-16	@admin: when i search for guests to make a reservation, some people are hidden(on FF)	new	open
26	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-06-15				public	2015-06-16	@admin: add new guest on making reservation, type drop down has invalid data	new	open
25	Nacalle	administrator	Ihab Roshdy	normal	minor	4 hours		Development	2015-06-15				public	2015-06-15	@admin: when i choose people to be added in the list of reservation and press search again, they appear as new	new	open
22	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-06-08				public	2015-06-08	@vendor: i can't upload a photo with a guest	new	open
21	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-06-08				public	2015-06-08	@admin: when i add a guest with an image, image is not synced	new	open
19	Nacalle	administrator	Omar Khaled	normal	minor	4 hours		Development	2015-06-08				public	2015-06-08	@admin: when i edit a guest, first 0 is removed from the mobile number field	new	open
17	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-06-04				public	2015-06-04	@admin: on making a new reservation and i don't choose a head, i can't submit	new	open
14	Nacalle	administrator		normal	minor			Development	2015-06-02				public	2015-06-02	@admin : people name is a link and open 404 not found page	new	open
9	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-06-01				public	2015-06-01	@admin: festibval icon shall appear beside the events with more than 1 day	new	open
8	Nacalle	administrator	Omar Hammad	normal	major	2 days		Development	2015-06-01				public	2015-06-01	@admin: add place in create event is not working	new	open
6	Nacalle	administrator	Omar Hammad	normal	major	4 hours		Development	2015-06-01				public	2015-06-01	@admin: cancel an event is not working	new	open
5	Nacalle	administrator	Omar Khaled	normal	minor	4 hours		Development	2015-06-01				public	2015-06-01	@admin: when i create a new event without an image, a man's image is added to the event	new	open
4	Nacalle	administrator	Omar Hammad	normal	major	2 days		Development	2015-06-01				public	2015-06-01	@admin: there is no cancel all in events	new	open
3	Nacalle	administrator	Ihab Roshdy	normal	major	2 days		Development	2015-06-01				public	2015-06-01	@admin: events and places lazy scrolling loads events in endless loop on Firefox only	new	open
2	Nacalle	administrator	Omar Hammad	normal	minor	4 hours		Development	2015-06-01				public	2015-06-01	@admin: when i cancel an event, confirmation message is not valid	new	open