## Duration Estimate
Durations Estimate | Solution (1) (Registration & finishline tracking)
Project: Urban Race |  |  |  |  | Date: 23/6/2015
Activity | Resource(s) | Optimistic | Most Likely | Pessimistic | Estimated Activity Duration | Reserve
Receive PSD | Software Engineer | 8 | 16 | 24 | 16
Design Registration Form | Software Engineer | 8 | 16 | 24 | 16
Receiving UID in Check-in | Software Engineer | 8 | 16 | 24 | 16
UID Reader Testing | Software Engineer | 16 | 24 | 32 | 24
Registration Development | Software Engineer | 16 | 24 | 32 | 24
Assigning UID Development | Software Engineer | 8 | 16 | 24 | 16
Receive finish line records | Subcontractor |  |  |  | 0
Assigning records to contestants | Software Engineer | 16 | 24 | 32 | 24
Secure hosting and servers | IT |  |  |  | 0
Securing Onsite registration | Software Engineer |  |  |  | 0
Securing Antenna’s and readers | Subcontractor |  |  |  | 0
Registration testing | Software Engineer | 4 | 8 | 16 | 8.6667
Check in testing | Software Engineer | 4 | 8 | 16 | 8.6667
Post finishline installation testing | Software Engineer | 4 | 8 | 16 | 8.6667
Total Number of hours |  | 92 | 160 | 240 | 162 | 0
Durations Estimate | Solution (2) (Registration & finishline tracking & Barcode reader)
Project: Urban Race |  |  |  |  | Date: 23/6/2015
Activity | Resource(s) | Optimistic | Most Likely | Pessimistic | Estimated Activity Duration | Reserve
Receive PSD | Software Engineer | 8 | 16 | 24 | 16
Design Registration Form | Software Engineer | 8 | 16 | 24 | 16
Receive & verify ticket number for activation | Software Engineer | 8 | 16 | 24 | 16
Receiving UID in Check-in | Software Engineer | 8 | 16 | 24 | 16
UID Reader Testing | Software Engineer | 16 | 24 | 32 | 24
Registration Development | Software Engineer | 16 | 24 | 32 | 24
Verify ticket activation | Software Engineer | 16 | 24 | 32 | 24
Assigning UID Development | Software Engineer | 8 | 16 | 24 | 16
Receive finish line records | Subcontractor |  |  |  | 0
Assigning records to contestants | Software Engineer |  |  |  | 0
Secure hosting and servers | IT | 8 | 16 | 24 | 16
Securing Onsite registration | Software Engineer | 8 | 16 | 24 | 16
Securing Antenna’s and readers | Subcontractor |  |  |  | 0
Registration testing | Software Engineer | 8 | 8 | 8 | 8
Check in testing | Software Engineer | 8 | 8 | 8 | 8
Post finishline installation testing | Software Engineer | 8 | 16 | 24 | 16
Total Number of hours |  | 128 | 216 | 304 | 216 | 0

## Activity cost estimate
Cost Estimate | Solution (1) (Registration & Finishline tracking)
Project: Urban Race |  |  |  |  | Date: 23/6/2015
WBS Activity | HR Resources | Equipment | Material | Logistics | Reserve | Assumptions / Constraints | Confidence Level | Estimate
Receive PSD | Software Engineer |  |  |  |  | Designed by Stallions
Design Registration Form | Software Engineer |  | Form Design |  |  | Domain to be decided
Receiving UID in Check-in | Software Engineer |  |  |  |  | Zabatnee admin deployed
UID Reader Testing | Software Engineer | UID Reader | RFID Bracelets
Registration Development | Software Engineer
Support offline & online Syncing | Software Engineer | Web server
Assigning UID Development | Software Engineer | UID Reader | RFID Bracelets
Receive finish line records | Subcontractor | UHF Antenna | RFID Bracelets
Assigning records to contestants | Software Engineer
Secure hosting and servers | IT
Securing Onsite registration | Software Engineer | Hardware | Connectors
Securing Antenna’s and readers | Subcontractor
Registration testing | Software Engineer
Check in testing | Software Engineer
Post finishline installation testing | Software Engineer | UHF Antenna | RFID Bracelets | Accomodation |  | Antenna range set by subcontractor
|  | UID Reader |  | Transportation
Power Supply
Total Number of hours | [5 empty] | 0 | 0 | 0
Cost Estimate | Solution (2) (Registration & Finishline tracking & Barcode reader)
Project: Urban Race |  |  |  |  | Date: 23/6/2015
WBS Activity | HR Resources | Equipment | Material | Logistics | Reserve | Assumptions / Constraints | Confidence Level | Estimate
Receive PSD | Software Engineer |  |  |  |  | Designed by Stallions
Developing Registration Form | Software Engineer |  | Form Design |  |  | Domain to be decided
Receive & verify ticket number for activation | Software Engineer |  | Ticket numbers
Receiving UID in Check-in | Software Engineer |  |  |  |  | Zabatnee admin deployed
UID Reader Testing | Software Engineer | UID Reader | RFID Bracelets
Registration Development | Software Engineer
Support offline & online Syncing | Software Engineer | Web Server
Verify ticket activation | Software Engineer | Bar code reader
Assigning UID Development | Software Engineer | UID Reader | RFID Bracelets
Receive finish line records | Subcontractor | UHF Antenna | RFID Bracelets
Assigning records to contestants | Software Engineer |  |  |  |  | Records received from Antenna
Secure hosting and servers | IT
Securing Onsite registration | Software Engineer | Hardware | Connectors
Securing Antenna’s and readers | Subcontractor
Registration testing | Software Engineer
Check in testing | Software Engineer
Post finishline installation testing | Software Engineer |  |  |  |  | Antenna range set by subcontractor
Total Number of hours | [5 empty] | 0 | 0 | 0